## Asr info
CEF | Transport
Action Code | 2015-SK-TM-0200-W
Exercise Year | 2023
Version | 1
Actual Action Start Date | 17/02/2016
Actual Action End Date | 31/12/2023
A. Maximum EU contribution (Art. 3) | €77,619,765.62
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €38,809,882.81
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €62,095,812.50
E. Sum of Previous Pre-financing Payments | €38,809,882.81
F. Sum of Interim Payments | €9,962,514.25
G. Sum of pre-financing and interim payments (E+F) | €48,772,397.06

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2015-SK-TM-0200-W (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Preparation of project documentation | 79.76
1 | Železnice Slovenskej republiky |  | 108582 | 108582 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total for activity 1
| 2 Engineering/construction works supervision | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157440 | 157440 | 448950 | 448950 | 404055 | 448950 | 35055 | 448950
Total for activity 2
| 3 Modernisation and construction of the railway line and equipment | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13950986 | 10152039.78 | 53207920 | 34765882.09 | 28688669 | 22893810.04 | 0 | 28961034.72
Total for activity 3
| 4 Project management | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145200 | 2350 | 145200 | 18500 | 24600 | 294150
Total for activity 4
Total eligible costs
1 | Železnice Slovenskej republiky
Total cumulated eligible costs
1 | Železnice Slovenskej republiky

## Financing needs (€)
Financing needs of the Action 2015-SK-TM-0200-W (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
1 Preparation of project documentation
1 | Železnice Slovenskej republiky
Totals for activity 1
2 Engineering/construction works supervision
1 | Železnice Slovenskej republiky
Totals for activity 2
3 Modernisation and construction of the railway line and equipment
1 | Železnice Slovenskej republiky
Totals for activity 3
4 Project management
1 | Železnice Slovenskej republiky
Totals for activity 4
Total financing needs
1 | Železnice Slovenskej republiky
Total cumulated financing needs
1 | Železnice Slovenskej republiky

## Progress Overview
Progress Overview of the Action 2015-SK-TM-0200-W (at accumulated level)
| 2016 |  |  | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 36 | 58 | 40 | 68 | 97 | 70 | 68 | 100 | 100 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 10 | 29 | 70 | 46 | 46 | 100 | 70 | 69 | 100 | 100 | 100
Activity 4 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 65 | 0 | 0 | 79 | 0 | 0 | 100 | 46 | 1 | 100 | 92 | 7 | 100 | 100 | 100 | 100
For the Action | 0 | 0 | 1 | 0 | 0 | 8 | 0 | 0 | 10 | 0 | 0 | 12 | 15 | 11 | 46 | 70 | 46 | 63 | 100 | 70 | 77 | 100 | 100 | 100