## Milestones
Modernisation of railway line Žilina – Košice, section Liptovský Mikuláš – Poprad-Tatry (outside), stage 1 (Poprad-Lučivná)
(2015-SK-TM-0200-W)
Table 1 Indicative completion dates of the milestones and technical progress
Activity | Milestone number | Milestone description | Indicative completion date |  |  |  |  | Means of verification | Technical progress1 (%)
|  |  | GA | ASR 2019 | ASR 2020 | ASR 2021 | ASR 2022
A1 | 1 | EIA consent decision issued | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | 2018-05-03 | EIA consent decision issued by Ministry of Environment | 30 | 100 | 5 | 100
A1 | 2 | Documentation for construction execution for Svit underpass | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | 2016-11-15 | Taking-over certificates | 35
A1 | 3 | Documentation for selection of a contractor | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | 2016-12-01 | Taking Over certificates | 35
A2 | 4 | Start of construction works supervision | 2020-08-26 | 2020-07-01 | 2020-08-26 | 2020-08-26 | 2020-08-26 | Notification by beneficiary | 1 | 100 | 20
A2 | 5 | Interim Supervision report | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2020-12-31 | 2020-12-31 | Supervision report | 25
A2 | 6 | Interim Supervision report | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2021-12-31 | 2021-12-31 | Supervision report | 42
A2 | 7 | Completion of construction works supervision | 2023-04-07 | 2022-07-31 | 2023-04-07 | 2023-11-30 | 2023-12-31 | Supervision report | 32
A3 | 8 | Start of preliminary construction works | 2020-07-07 | 2020-07-01 | 2020-07-07 | 2020-07-07 | 2020-07-07 | Notification by beneficiary | 5 | 100 | 60
A3 | 9 | Start of construction works | 2020-07-07 | 2020-08-01 | 2020-07-07 | 2020-07-07 | 2020-07-07 | Notification by beneficiary | 5
A3 | 10 | Completion of works on CPC 403 Svit - Lučivná (Štrba) | 2022-08-07 | 2021-03-31 | 2022-08-07 | 2023-05-20 | 2023-11-30 | Notification by Engineering Supervisor | 18
A3 | 11 | Completion of works on CPC 401 Poprad - Svit | 31.07.20212 | 2022-03-31 | 31.07.20212 | 2022-12-22 | 2023-08-31 | Notification by Engineering Supervisor | 37
A3 | 12 | Completion of works on CPC 402 Svit station | 31.03.20222 | 2022-07-31 | 2022-03-31 | 2023-05-31 | 2023-11-30 | Notification by Engineering Supervisor | 32
A3 | 13 | Completion of construction works | 07.08.20223 | 2022-07-31 | 07.08.20223 | 2023-05-31 | 2023-11-30 | Taking Over certificate | 2
A3 | 14 | "As-built" documentation completed | 2022-08-31 | 2022-07-31 | 2022-08-31 | 2023-05-31 | 2023-11-30 | Copy of "As-built" design - Taking Over certificate | 1
A4 | 15 | Public procurement procedure for construction works supervision published | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | 2018-09-10 | Contract Notice published in OJEU | 15 | 100 | 15
A4 | 16 | Contract signed for construction works supervision | 2020-07-30 | 2020-06-30 | 2020-07-30 | 2020-07-30 | 2020-07-30 | Signed contract | 15
A4 | 17 | Public procurement procedure for construction works published | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | 2017-06-30 | Contract Notice published in OJEU | 25
A4 | 18 | Contract signed for construction works | 2020-06-11 | 2020-06-30 | 2020-06-11 | 2020-06-11 | 2020-06-11 | Signed contract | 25
A4 | 19 | Public procurement procedure for publicity billboards published | 2020-06-19 | 2020-04-15 | 2020-06-19 | 2020-06-19 | 2020-06-19 | Contract Notice published in OJEU | 10
A4 | 20 | Contract signed for publicity billborads | 2020-06-24 | 2020-06-30 | 2020-06-24 | 2020-06-24 | 2020-06-24 | Signed contract | 10
1 The percentage rating of technical progress is assigned to every milestone within each activity.
(percentuálne hodnotenie technického pokroku je priradené ku každému míľniku v rámci každej aktivity)
2 the date applies to completion of the main part of construction works; all the construction works will be completed by 07.08.2022
(dátum sa vzťahuje na ukončenie hlavnej časti stavebných prác; celá konštrukcia)
3 the date applies to completion of construction works in all CPCs (CPC 401, CPC 402 and CPC 403)
(dátum platí pre ukončenie stavebných prác vo všetkých UČS (UČS 401, UČS 402 a UČS 403))