## Asr info
CEF | Transport
Action Code | 2015-SK-TM-0200-W
Exercise Year | 2023
Version | 1
Actual Action Start Date | 2016-02-17
Actual Action End Date | 2024-05-30
A. Maximum EU contribution (Art. 3) | €77,619,765.62
B. Pre-financing rate (Art. 4.1.2) | 50%
C. Maximum pre-financing payment (Art. 4.1.2) (=B*A) | €38,809,882.81
D. Maximum ceiling for the sum of pre-financing and interim payments (Art 4.1.3) (=80%*A) | €62,095,812.50
E. Sum of Previous Pre-financing Payments | €38,809,882.81
F. Sum of Interim Payments | €9,962,514.25
G. Sum of pre-financing and interim payments (E+F) | €48,772,397.06

## Eligible costs (€)
Update of the indicative breakdown of estimated eligible costs of the Action 2015-SK-TM-0200-W (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Preparation of project documentation | 79.76
1 | Železnice Slovenskej republiky |  | 108582 | 108582 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 108582 | 108582 | 0%
|  | Total for activity 1 | 108582 | 108582 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108582 | 108582 | 0%
| 2 Engineering/construction works supervision | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157440 | 157440 | 448950 | 448950 | 404055 | 448950 | 35055 | 448950 | 1045500 | 1504290 | 43.88%
|  | Total for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 157440 | 157440 | 448950 | 448950 | 404055 | 448950 | 35055 | 448950 | 1045500 | 1504290 | 43.88%
| 3 Modernisation and construction of the railway line and equipment | 79.76
1 | Železnice Slovenskej republiky |  | 0 |  | 0 |  | 0 |  | 0 |  | 13950986 | 10152039.78 | 53207920 | 34765882.09 | 28688669 | 22893810.04 | 0 | 28961034.72 | 95847575 | 96772766.63 | 0.9653%
|  | Total for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13950986 | 10152039.78 | 53207920 | 34765882.09 | 28688669 | 22893810.04 | 0 | 28961034.72 | 95847575 | 96772766.63 | 0.9653%
| 4 Project management | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145200 | 2350 | 145200 | 18500 | 24600 | 294150 | 315000 | 315000 | 0%
|  | Total for activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 145200 | 2350 | 145200 | 18500 | 24600 | 294150 | 315000 | 315000 | 0%
| Total eligible costs |  | 108582 | 108582 | 0 | 0 | 0 | 0 | 0 | 0 | 14108426 | 10309479.78 | 53802070 | 35217182.09 | 29237924 | 23361260.04 | 59655 | 29704134.72 | 97316657 | 98700638.63 | 1.422%
1 | Železnice Slovenskej republiky |  | 108582 | 108582 | 0 | 0 | 0 | 0 | 0 | 0 | 14108426 | 10309479.78 | 53802070 | 35217182.09 | 29237924 | 23361260.04 | 59655 | 29704134.72 | 97316657 | 98700638.63 | 1.422%
| Total cumulated eligible costs |  | 108582 | 108582 | 108582 | 108582 | 108582 | 108582 | 108582 | 108582 | 14217008 | 10418061.78 | 68019078 | 45635243.87 | 97257002 | 68996503.91 | 97316657 | 98700638.63 | 97316657 | 98700638.63 | 1.422%
1 | Železnice Slovenskej republiky |  | 108582 | 108582 | 108582 | 108582 | 108582 | 108582 | 108582 | 108582 | 14217008 | 10418061.78 | 68019078 | 45635243.87 | 97257002 | 68996503.91 | 97316657 | 98700638.63 | 97316657 | 98700638.63 | 1.422%

## Financing needs (€)
Financing needs of the Action 2015-SK-TM-0200-W (€)
|  |  | 2016 |  | 2017 |  | 2018 |  | 2019 |  | 2020 |  | 2021 |  | 2022 |  | 2023 |  | Total
| Activity name | Funding rate (%) | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Latest GA in force | Current ASR | Lastest GA in force | Current ASR | Deviation (%)
| 1 Preparation of project documentation | 79.76
1 | Železnice Slovenskej republiky |  | 86605.0032 | 86605.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86605.0032 | 86605.0032 | 0%
|  | Totals for activity 1 | 86605.0032 | 86605.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 86605.0032 | 86605.0032 | 0%
| 2 Engineering/construction works supervision | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125574.144 | 125574.144 | 358082.52 | 358082.52 | 322274.268 | 358082.52 | 27959.868 | 358082.52 | 833890.8 | 1199821.704 | 43.88%
|  | Totals for activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125574.144 | 125574.144 | 358082.52 | 358082.52 | 322274.268 | 358082.52 | 27959.868 | 358082.52 | 833890.8 | 1199821.704 | 43.88%
| 3 Modernisation and construction of the railway line and equipment | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11127306.4336 | 8097266.9285 | 42438636.992 | 27729267.555 | 22882082.3944 | 18260102.8879 | 0 | 23099321.2927 | 76448025.82 | 77185958.6641 | 0.9653%
|  | Totals for activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11127306.4336 | 8097266.9285 | 42438636.992 | 27729267.555 | 22882082.3944 | 18260102.8879 | 0 | 23099321.2927 | 76448025.82 | 77185958.6641 | 0.9653%
| 4 Project management | 79.76
1 | Železnice Slovenskej republiky |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115811.52 | 1874.36 | 115811.52 | 14755.6 | 19620.96 | 234614.04 | 251244 | 251244 | 0%
|  | Totals for activity 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 115811.52 | 1874.36 | 115811.52 | 14755.6 | 19620.96 | 234614.04 | 251244 | 251244 | 0%
| Total financing needs |  | 86605.0032 | 86605.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 11252880.5776 | 8222841.0725 | 42912531.032 | 28089224.435 | 23320168.1824 | 18632941.0079 | 47580.828 | 23692017.8527 | 77619765.6232 | 78723629.3713 | 1.422%
1 | Železnice Slovenskej republiky |  | 86605.0032 | 86605.0032 | 0 | 0 | 0 | 0 | 0 | 0 | 11252880.5776 | 8222841.0725 | 42912531.032 | 28089224.435 | 23320168.1824 | 18632941.0079 | 47580.828 | 23692017.8527 | 77619765.6232 | 78723629.3713 | 1.422%
| Total cumulated financing needs |  | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 11339485.5808 | 8309446.0757 | 54252016.6128 | 36398670.5107 | 77572184.7952 | 55031611.5186 | 77619765.6232 | 78723629.3713 | 77619765.6232 | 78723629.3713 | 1.422%
1 | Železnice Slovenskej republiky |  | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 86605.0032 | 11339485.5808 | 8309446.0757 | 54252016.6128 | 36398670.5107 | 77572184.7952 | 55031611.5186 | 77619765.6232 | 78723629.3713 | 77619765.6232 | 78723629.3713 | 1.422%

## Progress Overview
Progress Overview of the Action 2015-SK-TM-0200-W (at accumulated level)
| 2016 |  |  | 2017 |  |  | 2018 |  |  | 2019 |  |  | 2020 |  |  | 2021 |  |  | 2022 |  |  | 2023
| Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress | Financial Progress |  | Technical Progress
Activity name | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR | Latest GA | Current ASR | Current ASR
Activity 1 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 0 | 100 | 100 | 100
Activity 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 26 | 36 | 58 | 100 | 68 | 97 | 100 | 68 | 100 | 100 | 100
Activity 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 23 | 29 | 70 | 100 | 29 | 100 | 100 | 69 | 100 | 100 | 100
Activity 4 | 0 | 0 | 0 | 0 | 0 | 43 | 0 | 0 | 65 | 0 | 0 | 79 | 0 | 100 | 100 | 46 | 100 | 0 | 92 | 100 | 0 | 100 | 100 | 100
For the Action | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 23 | 0 | 70 | 100 | 0 | 100 | 100 | 75 | 100 | 100 | 100