Risk Assessment Grid

| Activity N° / Risk category | Risk | Impact (High/Low) | Likelihood (High/Low) | Control (Under/Beyond) | Mitigating measure(s) |
| --- | --- | --- | --- | --- | --- |
| 4 / Public procurement procedure | Deficiencies in the tender documentation for the procurement procedure | High | Low | Under | The competent personnel of ŽSR has been involved in public contracting at the tender documentation stage; If needed, a third-party consultancy company will be invited to verify the correctness of the tender documentation (technical and legal supervision over the tender documentation). |
|  | Selection of a sufficiently experienced contractor with the required capacity for performing the works | High | Low | Under | Precise determination of the conditions for the tender documentation (documented references, financial guarantees, sanctions, etc.). |
|  | High total price of works proposed by the preferred bidder | High | Low | Beyond | Precise determination of the conditions for the tender documentation (e.g. ceiling of the total costs). |
| 4 / Public procurement procedure (construction works, project management and audit support) | Obstructions and the use of appeals | High | High | Beyond | Increased control of the tender documents and the participation conditions. No mitigation measures can be executed by ŽSR within the public procurement procedure in terms of objections and the use of appeals. |
| 4 / Contract signed for construction works, construction works supervision, project management and audit support | Recommendation not to conclude the contract / Cancellation of public procurement procedure by Public Procurement Office | High | Low | Beyond | The MoTC SR may not recommend to conclude the contract after the inspection of the PP. The PPO may, within the control of the PP before signing the contract, order the cancellation of the PP if it finds out violation of the PPA in the PP process. The ŽSR have the right to appeal against such a decision. Measures for such a risk cannot be proposed, as the PPO and the MoTC SR are separate institutions and ŽSR do not affect their decisions. However, the ŽSR do not anticipate such a situation, as the PP preparation as well as the entire PP process is/will be carried out in accordance with the PPA. |
| 4 | Poor-quality project management | High | Low | Under | Creating a sufficiently competent and experienced project team covering all project areas and stages, and possibly also ensuring a third-party consultancy. Setting an effective organisational structure and internal project processes. |
| 4 | Price increase by the contractor during implementation | High | Low | Beyond | Precise setting of the contract with the contractor containing a procedure for the given case. |
| 4 | Delays in building proceeding | High | High | Beyond | Proactive engineering works in cooperation with ŽSR with the aim to setup cooperation with related construction authorities, alternatively municipalities and existence of effective tools for negotiation with land owners |
| 3 | Delays in construction works execution | Low | High | Beyond | Ensuring high quality of detail design documentation and creating a sufficiently competent and experienced project team covering all project areas and stages. Setting an effective organizational structure and internal project processes. Proactive monitoring and reporting of progress of works including risk reporting, setup of mitigation measures for recognized risks and its application |